Darcovský program Philip Morris 2015/2016

Report v 2016

Darcovský program Philip Morris sa zameriava na podporu organizácii pracujúcimi s ľuďmi bez domova.

V roku 2015/2016 bol grant vo výške 45 100 USD, teda 39561,4 Eur rozdelený na projektové náklady: 35900 a správu program vo výške 3661,4 Eur.

Projekty boli podporené priamou podporou:

- Filip-divadlom proti sociálno-kultúrnemu vylúčeniu ľudí bez domova, Divadlo bez domova, 5 900,00 €

- Podpora ľudí bez domova v útulkoch Depaul Slovensko, Depaul Slovensko 	13 000,00 €

- DOMEC - denné nízkoprahové a integračné centrum, OZ Vagus 	12 000,00 €

- Advokáti Pro Bono, Nadácia Pontis 5 000,00 €

The goals and objectives of the program was to solving the issue of homelessness as a state of extreme removal from society. This requires the upkeep of the existing projects of professional help and further development of a complex system of services to the homeless people, giving them a real chance to stand on their own two feet again and find replacement housing. Therefore we decided to support these four projects:

OZ Vagus - project DOMEC. Services provided: daily low-threshold center - social counseling, free

meals (breakfast, lunch) hygienic center, distribution of clothes, medical and nursing care, social assistance in handling institutional matters, leisure activities (trips, cinema etc.), internet for homeless people; Integration center - integration program to prepare the person for supported employment jobs (e.g. Dobre&Dobré coffee house), comprehensive individual management of the social situation of the client, offering jobs (internal or external), providing training in the area of education and social skills

Depaul Slovakia - Support for homeless people in shelters. Service provided: basic services (food, lodging, social assistance), individual work with clients (assistance services, social counseling, individual plans for clients).

Theatre With No Home - theatre against social and cultural exclusion of homeless people. Activities provided: regular drama therapeutic rehearsals, performing the rehearsed plays to the public (The Miracle Child, Kuca Paca, Puppet, Platea, The theatre of the oppressed), rehearsing of the new play in July 2016 and the subsequent premiere, activities aimed at sensitizing the public on the topic of homeless people.

Attorneys Pro Bono - tackling homelessness: increase the legal awareness, provide legal material for the purpose of public policy influencing and contribute to creating National Strategy on solving and prevention of homelessness in Slovakia.

Within the project of OZ Vagus we support the daily operation of low-threshold integration center Domec. Center provides services for homeless people in Bratislava. During the period of the project center providing services for approximately 80 clients per day - they are able to use social counseling services, showers, buy food for symbolic price (0,80 Eur per meal) and do some leisure activities. By linking the project with the activities of the social café DobreDobré, Vagus given the opportunity of employment to 50 clients.

In addition to basic services Domec also provided for clients with the assistance of social workers   social counseling and social supervision.

The project of DePaul Slovakia was focused on support of the operation of two . Shelter St. Louise de Marillac serves homeless people with chronical or acute diseases, people after hospital treatment or people with physically disabilities. During the project organization provide for clients beds, food, necessary assistance and 24-hours care. They are also provided necessary treatments, social assistance, transportation and access to medical help.

. Quantitative indicators (project period)

| Category | Expected results | Final results |
| --- | --- | --- |
| No. of clients of Shelter St. Louise de Marillac | 89 | 99 |
| No. of clients of Shelter St. Vincent de Paul | 61 | 69 |

The main goal of project of Theatre With No Home was to combat exclusion of homeless people, disable people and people with psychiatric diagnose via long-term drama-therapeutic process. During the project period repertory performed the rehearsed plays to the public (The Miracle Child, Kuca Paca, Puppet, Platea, The theatre of the oppressed), and prepared new performance called Flashback in July 2016. Each performance was a great chance for actors and actresses to meet people on different level. They were able to contribute to the society and offer to others different point of view on them.  After each performance there was space for a discussion with audience.

Quantitative indicators (project period)

| Category | Expected results | Final results |
| --- | --- | --- |
| No. of volunteers involved in the project | 2 | 2 |
| No. of volunteers working hours | 300 | 320 |
| No. of participants of the drama-therapeutic process (actors) | 14 | 14 |
| No. of theater performances | 8 | 8 |
| No. of theater rehearsals | 30 | 31 |
| No. of visitors | 500 | 600 |

Under the coordination of the program Attorneys Pro Bono a group of lawyers from different law firms (Attorneys Pro Bono members) and NGOs worked together on systemic changes in the rising homelessness problem in Slovakia. The early stages of the cooperation involved several NGOs working with homeless people as opposed to only one NGO, which is the usual case in the Pro Bono collaborations. This allowed the group to consider different points of view, exchange their experiences, and thus to define the necessary steps. Eventually focusing on the insolvency part of the problem, the cooperation in the last year centred on both the systemic improvement of the possibilities of debt relief for NINA (No Income No Assets) people as well as help with the insolvency proceedings of individual clients – homeless people.

Activities of the project

- Pro bono collaboration with the law firm White & Case New York - lawyers from offices in 6 countries researched and summarised the national Insolvency Codes pertinent to the NINA group. The Pro Bono group used the insolvency memos as an inspiration for proposing a reasonable system measures in Slovakia (Nov. 2015 – Mar. 2016)

- Consulting the proposal with other ministries (Ministry of Finance) and individual MPs

- Joining the working group at the Ministry of Justice, which was responsible for the amendment of both the provision on debt relief in the Act on Bankruptcy and Restructuring in the part concerning the Institute of Personal Bankruptcy as well as the Act on Legal Aid to Persons in Material Deprivation (May - June 2016)

- Successfully submitting comments on both of the proposed act amendments as a public commentator as well as through the comments of the Office of the Plenipotentiary for the Development of Civil Society (July 2016)

- Launch of the first Pro Bono Legal Homelessness Clinic in Europe (March 2016)

- We have an ongoing cooperation with the OZ Proti prúdu, working on legal materials, which can be used both by NGOs which work in the field as well as new lawyers and other subjects focusing on systemic change in the field.

- State any internal or external factors that influenced the project/program, both positive and negative. Describe actions being taken to alleviate negative factors or to sustain positive factors.

As we stated in part aimed to describe the project goals and objectives, supported projects had a large impact on the target group - homeless people.. Within the quantitative indicators from the organizations evidence of direct services, whether in the form of primary or additional services in the field of social counseling and assistance was provided to more than 1,700 clients. Of course, from the provided services benefits in some way the wider community of residents of the city – but it is difficult to quantify the impact.

Positive impact of the project is also in overcoming prejudices of major population about people living on the street - for example, the Theatre With No Home performances was attended by 600 visitors, a large number of customers has also visited DobreDobré cafe, where they can come into contact with homeless people on the road from the street.

The number of volunteers was involved in activities of organizations - either directly to the services provided by the individual facilities, or indirectly through pro bono services within the expert volunteering.

- What are your plans for sustaining this program or project?

All organization will continue their work after the project period. In the case of Depaul Slovakia, they are going to expand their help for homeless people. In 2015 the finished reconstruction of part of their nightshelter building and they have future plans to use these better living standards as motivation tool for Integration Program. The goal of the Program is to move people out of street to become independent. Those who will actively participate will have access to higher standards and Shelter St. Vincent de Paul will play a new and critical role in this system.

The project of Attorney Pro Bono will continue with the the collaboration between the lawyers and the NGO Proti prúdu. Furthermore, the discussions of the working group of the Ministry of Justice, which the group became a member of, revealed a need for a new social service and thus created an opportunity to advocate for a more prevention-based approach to insolvency. There is no social service providing financial literacy support to people in need of it, similarly as free legal advice centres provide help in legal matters. Such a service would not only be used in order to prevent people to take on further unreasonable financial obligations but it would also help assessing the amount of debts of people who wish to be relieved of their debts.

The Theater With No Home will continue they work to combat to combat exclusion of homeless people, disabled people, people with psychiatric diagnose - their actors and actresses, thanks to long-term drama therapeutic process. At the moment they will perform 5 different plays and the will develop a new one for the year 2017.